3GPP TSG-SA6 Meeting #67	S6-252021

# Fukuoka, Japan, 19th May 2025 - 23th May 2025 	                   (revision of S6-251023)

Source:	Airbus

Title:	Schedule for Rel-20 MCLOG_Ph2

Spec:	TR 23.700-39, all SA6 MC TSs

Agenda item:	9.2

Document for:	Discussion

Contact:	Jukka Vialen (jukka.vialen@airbus.com)

Abstract:

This living document provides the overall schedule and status for the Rel-20 Study on Logging and recording of mission critical services, Phase 2.

The schedule and target dates are for the SA6 work but status of related SIs/WIs in SA3, SA1 and CT1 is also included.

This document will be updated after every SA6 meeting until the “Logging and recording” work item is 100% ready.

The colour coding is: (Green: completed  /  Yellow: ongoing  / No highlight: not yet started)

# Rel-20 overall time plan for MCLOG_Ph2

- Feb 17-21

  - SA6#65

    - For agreement: SID – S6-250500 - agreed

    - For discussion: TR template, initial analysis of TR 23.784 for MCLOG_Ph2 – noted

  - SA3#120: MC WID proposal from Motorola - S3-250348 – postponed

  - CT1#153: Discussion paper from Motorola – C1-250066 -   noted

  - SA1#109: nothing

- Mar 12-14 SA plenary#107:

  - SA6 SID for approval - SP-250185 - approved

- April 7-11 SA6#66 (SA3#121, CT1#154)

  - SA6#66

    - For discussion: (Final) analysis of TR 23.784 for MCLOG_Ph2 – S6-251029 - noted

    - TR skeleton + structure + Annex A agreed ==> TR 23.700-39-010

  - SA3#121: minor correction in S3-251792

  - CT1#154: nothing

- May 19-23 SA6#67 (SA3#122, SA1#110)

  - SA6#67:

    - For approval: Scenarios, KIs, solutions, (solution evaluations)

    - For agreement: updated SID (adding interconnection to the scope)

  - SA3#122: FFS

  - CT1#156: FFS

  - SA1#110: FFS

- June 10-13 SA plenary#108		(SA3 Rel-20 MC WID for approval?)

- Aug 25-29 SA6#68, SA3#123, SA1#111     - KIs, solutions, solution evaluations

- Sep 16-19 SA#109		- SA6 TR for information (optional), SA6 WI for approval

- Oct 13-17 SA6#69, SA3#124	- Last meeting for solutions/solution evaluations (target: SI min 90% complete)

- Nov 17-21 SA6#70, SA3#125, SA1#112	- SI 100% complete, First normative CRs based on the agreed solutions

- Dec 9-12 SA plenary#109		- TR for approval

- Feb 9-13 (2026) SA6#71	- Last normative CRs based on agreed solutions, WI 100% complete

- Mar 9-13 (2026) SA plenary#110			- WI declared 100% complete

- April 13-17 (2026) SA6#72		- available for delayed topics and/or corrections

- May 18-22 (2026) SA6#73		- available for delayed topics and/or corrections

- June XX-YY (2026) SA plenary#111	 - Final 3GPP deadline for SA6 Rel-20 5GA work items