## Slide 1: SA6#68 Work Plan Review
Atle Monrad (InterDigital)
SA6 Chair
3GPP TSG-SA WG6 Meeting #68 S6-253793
Gothenburg, 25th – 29th August 2025

## Slide 2: Overview: Rel-20 Studies
Study Item | WI Code | SID Approved | SA6#67 | SA6#68 | Target Completion | Remarks
Study on Discreet listening and monitoring of mission critical services, Phase 2 | FS_MCDISC_Ph2 | SA#107 (03/2025) | 10% | 20% | SA#111 (03/2026) | 
Study on Logging and recording of mission critical services, Phase 2 | FS_MCLOG_Ph2 | SA#107 (03/2025) | 10% | 20% | SA#111 (03/2026) | 
Study on Service Enabler Architecture Layer (SEAL) Phase 4 | FS_SEAL_Ph4 | SA#105 (09/2024) | 75% | 95% | SA#110 (12/2025) | TR will be sent for approval
Study on Stage 2 for AI/ML service Phase 2 | FS_AIML_App_Ph2 | SA#107 (03/2025) | 40% | 60% | SA#110 (12/2025) | TR will be sent for information
Study on Application enabler for XR Services Phase 3 | FS_XRM_Ph3_APP | SA#107 (03/2025) | 35% | 70% | SA#110 (12/2025) | TR will be sent for information
Study on Stage 2 for MMTel Phase 2 | FS_MMTel_Ph2_APP | SA#107 (03/2025) | 30% | 40% | SA#111 (03/2026) | 
Study on SEAL data delivery Phase 3 | FS_SEALDD_Ph3 | SA#107 (03/2025) | 30% | 40% | SA#110 (12/2025) | 

## Slide 3: Overview: Rel-20 Studies
Study Item | WI Code | SID Approved | SA6#67 | SA6#68 | Target Completion | Remarks
Study on application enablement for satellite access enabled 5G services Phase 4 | FS_5GSAT_Ph4_APP | SA#108 (06/2025) | - | 10% | SA#111 (03/2026) | 
Study on application enablement for Ambient IoT services Phase 2 | FS_AmbientIoT_Ph2_APP | SA#108 (06/2025) | - | 10% | SA#111 (03/2026) | 
Study on Application user consent | FS_APCOT | SA#108 (06/2025) | - | 5% | SA#111 (03/2026) | 
Study of CAPIF Phase 4 | FS_CAPIF_Ph4 | SA#108 (06/2025) | - | 20% | SA#111 (03/2026) | 
Study on Application Enablement to support Energy Saving Phase 2 | FS_EnergySys_Ph2_APP | SA#108 (06/2025) | - | 15% | SA#111 (03/2026) | 
Study on use of Sensing results for Vertical Applications | FS_Sensing_APP | SA#108 (06/2025) | - | 15% | SA#111 (03/2026) | 

## Slide 4: Overview: Rel-20 Work-Items
Work Item | WI Code | WID Approved | SA6#67 | SA6#68 | Target Completion | Remarks
Stage 2 for Enhanced Mission Critical Services Architecture Phase 2 | enhMC_Ph2-MC | SA#107 (03/2025) | 15% | 30% | SA#112 (06/2026) | 
Stage 2 for FRMCS Phase 6 | FRMCS_Ph6 | SA#107 (03/2025) | 35% | 45% | SA#112 (06/2026) | 
Stage 2 for Mission Critical Services for UE-to-UE and UE-to-Network over multi-hop relay | MultiHop-MC | SA#107 (03/2025) | 75% | 75% | SA#111 (03/2026) | 
Stage 2 for mobile metaverse services Phase 2 | Metaverse_Ph2-APP | SA#107 (03/2025) | 45% | 65% | SA#110 (12/2025) | 
Guidelines for 3GPP Application Enablement usage | AppEnable_EXT | SA#108 (06/2025) | - | 5% | SA#111 (03/2026) | 

## Slide 5: Conference calls and other items
Rapporteurs to make the draft TRs/TSs available Wednesday September 3rd 23:00 UTC
All documents must be uploaded before End-of-Meeting
Pre-SA6#69 conference calls (Dates are TBD) – Maximum 2 hours/call and 1 hour/topic
  Potential Topics
  Date Exclusions
    ??

## Slide 6: SA6 Rel-20 6G-study planning
 | SA6#68 (Aug 25-29) | Moderated Discussion#1 (Sep 1 to 14) | SA6#69 (Oct 13-17) | Moderated Discussion#2 () | SA6#70 (Nov 17-21) | Post SA6#70 untill end of Study
Input | 1. Company proposed work tasks and initial analysis SA1 TR 22.870. 2. Discussion on Working methods (NWM, email, conf calls) for Moderated discussions. 3. Discuss the questions for Moderated Discussions | Candidate Work Tasks from SA6#68 Dates: Sep 1 to 14 (2 weeks) | 1. Moderator collated Work Tasks 2. Company proposed Work Tasks to SA6#69 | Candidate Work Tasks from SA6#69 Dates: Oct 20 to 26 (1 week) | 1. Moderator collates Work Tasks 2. Company proposed Work Tasks to SA6#70 | Company proposed key issues, solutions etc. to the agreed Work-Tasks
Output | 1. Populate candidate Work Tasks 2. Finalize tool and plan for Moderated Discussions. 3. Agree to questions for Moderated Discussions | Moderator collates Work Tasks and prepares discussion summary | Intermediate SID based on the agreed Work Tasks (Round 1) | Moderator collates Work Tasks and prepares discussion summary | Finalize Work Tasks (Round 2). Finalize SID considering agreed Work Tasks and submit for SA plenary approval | Finalize TR with relevant Key Issues, Solutions and Conclusions for all Work Tasks by end of release. The conclusions of this study will form the basis for normative 6G application enablement work.

## Slide 7: SA6 meeting schedule
Meeting | Date | Location
2025 |  | 
SA6#69 | 13 – 17 October 2025 | Wuhan, China
SA6#70 | 17 – 21 November 2025 | Dallas (TX), USA
2026 |  | 
SA6#71 | 9 – 13 Feb 2026 | India, Location TBC
SA6#72 | 13 – 17 April 2026 | EU, Location TBC
SA6#73 | 18 – 22 May 2026 | China, Location TBC
SA6#74 | 24 – 28 August 2026 | Prague, Czech Republic
SA6#75 | 12 – 16 October 2026 | Prague, Czech Republic
SA6#76 | 16 – 20 November 2026 | Calgary, Canada

## Slide 8: Thank You!