## FDD RRM Completion tracker
RM test TS34.121 Rel 5 (All FDD Rel.) | [6 empty] | T1 Current status at release No. |  |  |  |  | 5.2.0 |  | %"Good to Go"
Use only "1" for YES (complete, or no need), "0" for NO (incomplete) to allow Automatic Completion Percentage calculation. There should be no 'FFS', no square brackets, all quantities reported to the System simulator should be in measurement units, not dBm, and tolerancing should include statistical effects if needed. With a '1' in all the columns, test "complete" becomes set, and percentage ready for GCF is increased. michael.page-jones@roke.co.uk |  |  |  | Core Spec TS25.133 RAN4 latest state |  |  | T1 Spec | AUTOMATIC CALCULATION OF COMPLETION PLEASE USE ONLY "1" for "YES" complete or not needed, PLEASE USE ONLY "0" for "NO" for incomplete or something missing | [6 empty] | 20
TEST # | GCF Batch | Section |  | Clause No. in Annex | Test Case Available | RAN 4 last CR no | T1&T1R CR numbers | Test Tol. included ? (Annex F.1.5) | Statistical Testing included | FFS removed | TBD & [] removed | Reports not dB but UE measured units? | Any Clause Present in 34.121 ? | Test should be present | Complete for GCF
|  | 8.2 | Idle Mode Tasks | A.4 | -
1 |  | 8.2.1 | Cell Selection | A.4.1 | -
|  | 8.2.2 | Cell Re-Selection | A.4.2 | - |  | T1R020212
2 | 1 | 8.2.2.1 | Scenario 1: Single carrier case | A.4.2.1 | Y |  |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0
3 | 1 | 8.2.2.2 | Scenario 2: Multi carrier case | A.4.2.2 | Y |  |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0
|  | 8.2.3 | UTRAN to GSM Cell Re-Selection | A.4.3 | - |  | T1R020141 T1R020212 | -
4 | 1 | 8.2.3.1 | Scenario 1: Both UTRA and GSM level changed | A.4.3.1 | Y |  |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0
5 | 1 | 8.2.3.2 | Scenario 2: Only UTRA level changed | A.4.3.2 | Y |  |  | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0
6 |  | 8.2.4 | FDD/TDD Cell Re-selection | A.4.3.3 | Y |  |  | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0
|  | 8.3 | UTRAN Connected Mode Mobility | A.5 | -
7 | 2.1 | 8.3.1 | FDD/FDD Soft Handover | A.5.1 | Y |  | T1R020110r3 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0
|  | 8.3.2 | FDD/FDD Hard Handover | A.5.2 | -
8 | 2.1 | 8.3.2.1 | FDD/FDD Hard Handover to intra-frequency cell | A.5.2.1 | Y |  | T1R020070 T1R020139 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0
9 | 2.2.1 | 8.3.2.2 | FDD/FDD Hard Handover to inter-frequency cell | A.5.2.2 | Y |  | T1R020070 T1R020139 T1R020213 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0
10 |  | 8.3.3 | FDD/TDD Handover | A.5.3 | Y |  | T1R020138, T1R020221 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0
11 | 2.2.1 | 8.3.4 | Inter-system Handover from UTRAN FDD to GSM | A.5.4 | Y |  | T1R020140 T1R020212 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0
|  | 8.3.5 | Cell Re-selection in CELL_FACH | A.5.5 | - |  | T1R020212
12 | 1 | 8.3.5.1 | One frequency present in neighbour list | A.5.5.1 | Y |  | T1R020111r3 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0
13 | 1 | 8.3.5.2 | Two frequencies present in the neighbour list | A.5.5.2 | Y |  | T1R020112r3 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0
14 | 2.2.1 | 8.3.5.3 | Cell Reselection to GSM | A.5.5.3 | Y |  | T1R020138 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0
|  | 8.3.6 | Cell Re-selection in CELL_PCH | A.5.6 | -
15 | 2.2.2 | 8.3.6.1 | One frequency present in the neighbour list | A.5.6.1 | Y |  | T1R020204 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0
16 | 2.2.2 | 8.3.6.2 | Two frequencies present in the neighbour list | A.5.6.2 | Y |  | T1R020204 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0
|  | 8.3.7 | Cell Re-selection in URA_PCH | A.5.7 | - |  | T1R020212
17 | 2.2.2 | 8.3.7.1 | One frequency present in the neighbour list | A.5.7.1 | Y |  | T1R020142 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0
18 | 2.2.2 | 8.3.7.2 | Two frequencies present in the neighbour list | A.5.7.2 | Y |  | T1R020142 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0
|  | 8.4 | RRC Connection Control | A.6 | -
|  | 8.4.1 | RRC Re-establishment delay | A.6.1 | -
19 | 2.1 | 8.4.1.1 | Test 1 | A.6.1.2.1 | Y |  | T1R020143 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0
20 | 2.1 | 8.4.1.2 | Test 2 | A.6.1.2.2 | Y |  | T1R020143 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0
|  | 8.4.2 | Random Access | A.6.2 | -
21 | 2.1 | 8.4.2.1 | Correct behaviour when receiving an ACK | A.6.2.2.1 | Y |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
22 | 2.1 | 8.4.2.2 | Correct behaviour when receiving an NACK | A.6.2.2.2 | Y |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
23 | 2.1 | 8.4.2.3 | Correct behaviour at Time-out | A.6.2.2.3 | Y |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
24 | 2.2.1 | 8.4.2.4 | Correct behaviour when reaching maximum transmit power | A.6.2.2.4 | Y |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | 8.4.3 | Transport format combination selection in UE | A.6.4 | Y
25 | 2.2.1 | 8.4.3.1 | Interactive or Background, PS, UL: 64 kbps | A.6.4 | Y |  | T1R020138 T1R020206 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0
|  | 8.5 | Timing and Signalling Characteristics | A.7 | -
26 | 2.1 | 8.5.1 | UE Transmit Timing | A.7.1 | Y |  | T1R020128 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | 8.6 | UE Measurements Procedures | A.8 | -
|  | 8.6.1 | FDD intra frequency measurements | A.8.1 | -
27 | 2.1 | 8.6.1.1 | Event triggered reporting in AWGN propagation conditions | A.8.1.1 | Y |  | T1R020087 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0
28 | 2.1 | 8.6.1.2 | Event triggered reporting of multiple neighbours in AWGN propagation condition | A.8.1.2 | Y |  | T1R020088 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0
29 | 2.1 | 8.6.1.3 | Event triggered reporting of two detectable neighbours in AWGN propagation condition | A.8.1.3 | Y |  | T1R020089 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0
30 | 2.2.1 | 8.6.1.4 | Correct reporting of neighbours in fading propagation condition | A.8.1.4 | Y |  | T1R020113 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0
|  | 8.6.2 | FDD inter frequency measurements | A.8.2 | - |  | T1R020162
31 | 2.1 | 8.6.2.1 | Correct reporting of neighbours in AWGN propagation condition | A.8.2.1 | Y |  | T1R020133 fading deletion | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0
|  | 8.6.3 | TDD measurements | A8.3 | -
32 |  | 8.6.3.1 | Correct reporting of TDD neighbours in AWGN propagation condition | A.8.3.1 | - |  | T1R030050 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 0
|  | 8.6.4 | GSM measurements | A.8.4 | Y
33 | 2.2.2 | 8.6.4.1 | Correct reporting of GSM neighbours in AWGN propagation condition | A.8.4.1 | Y |  | T1R020138 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | 8.7 | Measurements Performance Requirements | A.9 | -
|  | 8.7.1 | CPICH RSCP | A.9.1.1 | -
|  | 8.7.1.1 | Intra frequency measurements accuracy | A.9.1 | -
34 | 2.1 | 8.7.1.1.1 | Absolute accuracy requirement | A.9.1.1.1.1 | Y |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
35 | 2.1 | 8.7.1.1.2 | Relative accuracy requirement | see 9.1.1.1.2 (not annex) | Y |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | 8.7.1.2 | Inter frequency measurement accuracy | - | -
36 | 2.1 | 8.7.1.2.1 | Relative accuracy requirement | A.9.1.1.1.2 | Y |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | 8.7.2 | CPICH Ec/Io | A.9.1.2 | - |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | 8.7.2.1 | Intra frequency measurements accuracy | A.9.1.2.1 | -
37 | 2.1 | 8.7.2.1.1 | Absolute accuracy requirement | A.9.1.2.1.1 | Y |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
38 | 2.1 | 8.7.2.1.2 | Relative accuracy requirement | see 9.1.2.1.2 (not annex) | Y |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | 8.7.2.2 | Inter frequency measurement accuracy | - | -
39 | 2.1 | 8.7.2.2.1 | Void | -
40 | 2.1 | 8.7.2.2.2 | Relative accuracy requirement | A.9.1.2.1.3 | Y |  |  | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0
|  | 8.7.3 | UTRA Carrier RSSI | A.9.1.3 | -
41 | 2.1 | 8.7.3.1 | Absolute measurement accuracy requirement | A9.1.3.2 | Y |  |  | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0
42 | 2.1 | 8.7.3.2 | Relative measurement accuracy requirement | A9.1.3.2 | Y |  |  | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0
43 | 2.2.1 | 8.7.3A | GSM Carrier RSSI | A.9.1.3A | Y |  | T1R020138 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
44 | 2.2.1 | 8.7.3B | Transport channel BLER+D100 | A.9.1.3B NO TEST | N |  | T1R020138 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
45 | 1 | 8.7.3C | UE transmitted power | A.9.1.3C | Y |  | T1R020138 T1R020217 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0
|  | 8.7.4 | SFN-CFN observed time difference | A.9.1.4 | -
46 | 2.2.1 | 8.7.4.1 | Intra frequency measurement requirement | A.9.1.4.1.1 | Y |  | T1R020049 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0
47 | 2.2.1 | 8.7.4.2 | Inter frequency measurement requirement | A.9.1.4.1.2 | Y |  | T1R020049 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | 8.7.5 | SFN-SFN observed time difference | A.9.1.5 | -
48 | 2.2.1 | 8.7.5.1 | SFN-SFN observed time difference type 1 | A.9.1.5.1 | Y |  | T1R020050 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| 2.2.1 | 8.7.5.2 | SFN-SFN observed time difference type 2 | A.9.1.5.1.2 | Y |  | T1R020138 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
49 |  |  | Intra frequency measurement requirement accuracy without IPDL period active | A.9.1.5.2 | Y |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
50 |  |  | Intra frequency measurement requirement accuracy with IPDL period active | A.9.1.5.3 | Y |  | T1R020208 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
51 |  |  | Inter frequency measurement requirement accuracy | See 9.1.8.2.3 not annex | Y |  | T1R020209 | 0 | 0 |  |  |  |  | 1 | 0
|  | 8.7.6 | UE Rx-Tx time difference | A.9.1.6 | -
52 | 1 | 8.7.6.1 | UE Rx-Tx time difference type 1 | A.9.1.6.1 | Y |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
53 |  | 8.7.6.2 | UE Rx-Tx time difference type 2 | A.9.1.6.2 | Y |  | T1R030049 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
54 | 2.2.1 | 8.7.7 | Observed time difference to GSM cell | A.9.1.7 | N |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  | 8.7.8 | P-CCPCH RSCP | A.9.1.8 | -
55 |  | 8.7.8.1 | Absolute measurement accuracy | A.9.1.8.1 | Y |  |  | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0

## Notes
This worksheet is meant to calculate the competion of the RRM sections of 34.121 as a helper to show whciuh sections need attention. I am sure it will change. I am worried that we do not know how many times many tests must be done for our '90%' success with FFS confidence, this is the most common redline, along with 'repeat 'TBD times'. Our other areas that will be fun are when RAN4 have not made a prototype test -these in clude cell selection time, time difference to GSM, and Transport Channel BLER, and to some extent SFN SFN measurement accuracy. Otherwise lets turn red to green. Version 1 Mike Page-Jones Dec 2003, Siemens Roke Manor.