## Sheet1
Tdoc # | Order | Av. | Ag. I. | Source | Title | Type | TTCN | Summary | Discussion | Conclusion |  | Ag. I.
T1-040500 |  |  |  | TB Chairman | Agenda | [6 empty] | 8.8.3
T1-040501 | -1 |  | 8.3 | ETSI Secretariat | LS from GERAN regarding TSG-G3 change requests to test cases that are thought to be of interest to T1 |  |  |  |  | Withdrawn, replaced by T1-040763 and T1-040764
T1-040502 |  |  | 8.5.1 | Anite | Proposed change to PRD-12 on e-mail handling of TTCN CRs
T1-040503 |  |  | 8.8.11 | Rohde & Schwarz | Initial version of an iWD for TS 34.123 tests not ready for T1 approval |  |  |  |  | Noted. The concept and format are agreed with the following change: the package number of each test case is indicated.
T1-040504 |  | X | 8.8.4 | Anritsu Limited | Corrections to Package 2 test case 9.4.2.4 Procedure 2 |  |  |  |  | Revised in T1-040964
T1-040505 | -1 |  |  | Rohde & Schwarz | CR to 34.123-1 Rel-5: Correction to package 3 RRC test case 8.4.1.26 |  |  |  |  | Withdrawn
T1-040506 | -1 |  |  | Rohde & Schwarz | CR to TS 34.123-1 Rel-5: Correction to package 3 RRC test case 8.2.4.1a |  |  |  |  | Withdrawn
T1-040507 | -1 |  |  | Rohde & Schwarz | CR to 34.123-1 Rel-5: Correction to P3 RRC test case 8.2.4.1a |  |  |  |  | Withdrawn
T1-040508 |  | X | 8.8.3 | Ericsson | Correction to Approved RRC Package 1 TC 8.3.4.1, 8.3.4.2 and 8.3.4.3 | CR | H |  |  | Not agreed. Instead it was agreed to modify the ASP definition for "modify cell power" to an enumeration with an additonal vallue of "cell_off". The implementation of this is then up to the SS manufacturer.
T1-040509 |  | X | 8.8.3 | Ericsson, ETSI | Correction to low priority RRC TCs 8.1.8.3 and 8.2.1.13. | CR | L |  |  | Approved
T1-040510 |  | X | 8.7.1 | Ericsson, ETSI | CR to TS 34.108 R99: Correction to IEs START and ul_CounterSynchronisationInfo. | CR |  |  |  | Approved
T1-040511 |  | X | 8.7.1 | Ericsson, ETSI | CR to TS 34.108 Rel4: Correction to IEs START and ul_CounterSynchronisationInfo. | CR |  |  |  | Approved
T1-040512 |  | X | 8.7.2 | Ericsson, ETSI | CR to TS 34.108 Rel5: Correction to IEs START and ul_CounterSynchronisationInfo. | CR | N |  |  | Approved
T1-040513 |  | X | 8.8.3 | Ericsson, ETSI | Correction to low priority RRC TCs TC 8.1.6.4, 8.1.9a and 8.1.9b. | CR | L |  |  | Approved
T1-040514 |  | X | 8.8.6 | Nokia | Correction to Package 1 SM TC 11.3.1 RAB release location | CR |  |  |  | Revised in T1-040962 To move the comment field from step 7a to 7 and delete 7a.
T1-040515 |  | X | 8.8.6 | Nokia | Correction to Package 1 SM TC 11.3.2 RAB release location | CR |  |  |  | Revised in T1-040963, same as 514.
T1-040516 |  | X | 7.5.2 | Nokia | Follow-up Database for implementation of core specification CR's in TS 34.121
T1-040517 |  | X | 7.5.3 | Nokia | Follow-up Database for implementation of core specification CR's in TS 34.122
T1-040518 |  | X | RF/HSDPA | Nokia | Introduction of TC 9.3.2: Reporting of CQI in fading propagation conditions
T1-040519 |  | X | 8.8.2.1 | Ericsson | Correction to HSDPA MAC-hs test cases | CR | L |  |  | Approved
T1-040520 |  | X | 8.8.2.1 | Ericsson | New HSDPA MAC-hs reset test case | CR | L |  |  | Approved
T1-040521 |  | X | 8.8.8 | Ericsson | Correction to HSDPA radio bearer test cases | CR | N |  |  | Approved
T1-040522 |  | X | 8.7.2 | Ericsson | CR to 34.108 Rel-5: Correction to HSDPA reference radio bearer configurations | CR | L |  |  | Approved
T1-040523 |  | X | 7.5.5 (Test Tolerances) | Racal Instruments Wireless Solutions | TR 34.902 restructured for FDD expansion
T1-040524 |  |  | 7.5.4.2 (RRM Priority 2.1 test cases) | Racal Instruments Wireless Solutions | Introduction of Test Tolerances for RRM test 8.6.1.1
T1-040525 |  | X | 7.5.4.2 (RRM Priority 2.1 test cases) | Racal Instruments Wireless Solutions | Update of 34.902 for RRM test 8.6.1.1
T1-040526 |  | X | 8.8.4 | Anritsu Ltd | Corrections to Package 2 test case 9.4.2.4 Procedure 2 | CR |  |  |  | Replaced by T1-040504
T1-040527 |  | X | 8.8.7 | Nokia, MCC 160 | Correction to low priority GMM TC 12.4.1.5 | CR | L |  |  | Approved
T1-040528 |  | X | 8.8.7 | Nokia, MCC 160 | Correction to P4 GMM TCs 12.2.1.5d and 12.4.1.4d | CR | L |  |  | Approved
T1-040529 |  | X | 8.8.7 | Nokia, MCC 160 | Correction to several GMM TCs to include equivalent PLMN IE | CR | H |  | 2004-04-24 | Postponed to the email reflector to check if the Networks do or don't send the HPLMN of the UE in the equivalent PLMN list.
T1-040530 |  | X | 8.10.1 | MCC task 160 | GERAN generic procedures and TTCN encoding rules for CSN.1 specific encoding | CR |  |  |  | Revised in T1-040940
T1-040531 |  |  | 4.4 | MCC task 160 | MCC task 160 May report | INPUT REPORT
T1-040532 |  | X | 7.5.2 clause 6 | Racal Instruments Wireless Solutions | Proposed changes to Rx Spurious Emission test 6.8: summary
T1-040533 |  | X | 7.5.4.2 | Nokia | Corrections to CPICH RSCP test cases | CR
T1-040534 |  | X | 7.5.4.2 | Nokia | Corrections to CPICH Ec/Io test cases | CR
T1-040535 |  | X | 7.5.4.2 | Nokia | Corrections to UTRA Carrier RSSI test cases | CR
T1-040536 |  | X | 7.5.4.3 | Nokia | Corrections to SFN-CFN observed time difference test cases | CR
T1-040537 |  | X | 7.5.4.3 | Nokia | Corrections to SFN-SFN type 1 measurement test cases | CR
T1-040538 |  | X | 7.5.4.1 | Nokia | Corrections to UE Rx-Tx time difference type 1 test cases | CR
T1-040539 |  | X | 7.5.4.2 | Nokia | Corrections to FDD/FDD Soft Handover test cases | CR
T1-040540 |  | X | 7.7.6 | Nokia | Text proposal to TR 34.902 v1.1.0 to include the analysis of FDD/FDD soft handover test case | OTHER
T1-040541 |  | X | 7.5.4 | Nokia | Correction to MEASUREMENT CONTROL and MEASUREMENT REPORT messages | CR
T1-040542 |  | X | 7.5.4 | Nokia | Addition of unit for OCNS_Ec/Ior in RRM tests | CR
T1-040543 |  | X | 7.5.2 clause 6 | Racal Instruments Wireless Solutions | 34.121 revision of Test 6.8, Receiver Spurious Emissions
T1-040544 |  | X | 7.7.4: TS 34.108 (Rel-5) | Racal Instruments Wireless Solutions | 34.108 revision to Test 6.8, Receiver Spurious Emissions
T1-040545 |  |  | 6.8 | Ericsson | Work plan for HSDPA test cases – status before T1#23 | INFO
T1-040546 |  | X | 7.7.4 | Ericsson | CR to 34.108 Rel-5: Addition of test procedure for HSDPA RF testing | CR
T1-040547 |  | X | 8.8.7 | Sasken Communication Technologies Limited | Correction to GMM test case 12.9.3 to include CS registration. | CR |  |  |  | To be merged
T1-040548 |  | X | 8.8.9 | Sasken Communication Technologies Limited | Correction to Package III SMS Test Case 16.2.1 | CR |  |  |  | Revised in T1-040968
T1-040549 |  | X | 8.8.2.1 | Sasken Communication Technologies Limited | Correction to package 1 MAC testcase 7.1.2.3.1 | CR | N |  |  | Approved
T1-040550 |  | X | 8.8.2.2 | Sasken Communication Technologies Limited | Correction to GCF package 1 RLC testcase 7.2.3.27 | CR |  |  |  | Withdrawn, Merged
T1-040551 |  | X | 8.8.4 | Sasken Communication Technologies Limited | Correction to package 2 MM testcase 9.1 to align with TTCN implementation. | CR |  |  |  | Revised in T1-040956
T1-040552 |  | X | 8.8.4 | Sasken Communication Technologies Limited | Correction to package 2 MM testcase 9.4.2.1 to align with TTCN implementation. | CR | N |  |  | Approved
T1-040553 |  | X | 8.8.4 | Sasken Communication Technologies Limited | Correction to package 2 MM testcase 9.4.4 | CR | N |  |  | Approved
T1-040554 |  | X | 8.8.4 | Sasken Communication Technologies Limited | Correction to package 2 MM testcase 9.4.8 | CR |  |  |  | Withdrawn. Change included in T1-040948. R&S method agreed.
T1-040555 |  | X | 8.7.1 | Sasken Communication Technologies Limited | Physical channel parameters for AM RLC 7 bit Length Indicator TestCases (Rel-4) | CR |  |  |  | Approved
T1-040556 |  | X | 8.8.9 | Sasken Communication Technologies Limited | Correction of the Test Sequence for 16.1.1 to add more clarity. | CR |  |  |  | Merged in T1-040777
T1-040557 |  | X | 8.8.5 | Sasken Communication Technologies Limited, MCC Task 160 | ‘Emergency call establishment’ as one of the CM Service Type in 10.1.2.1.1 | CR | N |  |  | Approved
T1-040558 |  | X | 8.8.3 | Sasken Communication Technologies Limited | Correction to package 1 test case 8.1.2.9 for BCCH Modification Time in Paging Type 1 message | CR | N |  |  | Approved
T1-040559 |  | X | 8.8.3 | Sasken Communication Technologies Limited | Correction for RRC Transaction Identifier in test cases 8.1.5.1 and 8.1.5.4 | CR | N |  |  | Approved
T1-040560 |  | X | 8.8.3 | Sasken Communication Technologies Limited | Editorial corrections for 8.3.1.1 | CR | N |  |  | Approved
T1-040561 |  | X | 8.8.3 | Sasken Communication Technologies Limited | Corrections to prose for test cases 8.1.1.4, 8.1.1.5 and 8.1.1.6 | CR | N |  |  | Approved
T1-040562 |  | X | 8.8.3 | Sasken Communication Technologies Limited, MCC Task 160 | Corrections in Security Mode Command for 8.1.7.1 and 8.1.7.2 test cases. | CR |  |  |  | Withdrawn
T1-040563 |  | X | 8.7.1 | Sasken Communication Technologies Limited, MCC Task 160 | Corrections to the default contents of Security Mode Command (Rel-4) | CR |  |  |  | Approved
T1-040564 |  | X | 8.7.1 | Sasken Communication Technologies Limited, MCC Task 160 | Corrections to the default contents of Security Mode Command (R99) | CR |  |  |  | Approved
T1-040565 |  | X | 8.8.8 | Sasken Communication Technologies Limited | Editorial correction for 14.2.11, 14.2.39.2 | CR | N |  |  | Approved
T1-040566 |  | X | 8.8.3 | Sasken Communication Technologies Limited | Future compatibility of RRC critical extension testing | CR | N |  |  | Approved
T1-040567 |  | X | 8.8.3 | Sasken Communication Technologies Limited | Editorial correction for 8.3.1.31 | CR | N |  |  | Approved
T1-040568 |  | X | 8.8.3 | Sasken Communication Technologies Limited, MCC Task 160 | Corrections in Specific Message Contents for clause 8.3.1.5.4 and 8.3.1.6.4 | CR | H | W |  | Approved
T1-040569 |  | X | 8.7.1 | Sasken Communication Technologies Limited | Physical channel parameters for AM RLC 7 bit Length Indicator TestCases (R99) | CR |  |  |  | Approved
T1-040570 |  | X | 8.8.8 | Nokia | Addition of test case for Interactive or background / UL:64 DL:768 kbps / 10 ms TTI | CR | L |  |  | Approved
T1-040571 |  | X | 8.9.1 | Nokia, Nortel | New applicability statements | CR |  |  |  | Approved
T1-040572 |  | X | 8.7.1 | Ericsson | CR to 34.108 R99: Addition of generic test procedure for AS test cases using the test loop | CR |  |  |  | Revised as per 574, but no new CR generated
T1-040573 |  | X | 8.7.1 | Ericsson | CR to 34.108 Rel-4: Addition of generic test procedure for AS test cases using the test loop | CR |  |  |  | Revised as per 574, but no new CR generated
T1-040574 |  | X | 8.7.2 | Ericsson | CR to 34.108 Rel-5: Addition of generic test procedure for AS test cases using the test loop | CR |  |  |  | Revised in T1-040934
T1-040575 |  | X | 8.8.3 | Nokia UK and ETSI MCC160 | CR to 34.123-1 REL-5: Correction to package 4 RRC test case 8.2.2.35 | CR | N |  |  | Approved
T1-040576 |  | X | 8.8.3 | Nokia and ETSI MCC160 | CR to 34.123-1 REL-5: Correction to package 4 RRC test case 8.2.3.29 | CR | N |  |  | Approved
T1-040577 |  | X | 8.8.3 | Nokia and ETSI MCC160 | CR to 34.123-1 REL-5: Correction to package 2 RRC test case 8.3.1.22 | CR | N |  |  | Approved.
T1-040578 |  | X | 8.9.1 | Nokia and ETSI MCC160 | CR 34.123-2 Rel-5: Applicability of Package 2 RRC test cases 8.3.1.22 | CR |  |  |  | Approved
T1-040579 |  | X | 8.9.1 | CETECOM GmbH | Correction on applicability definition oftest cases 8.3.7 |  |  |  |  | Approved
T1-040580 |  | X | 8.8.3 | CETECOM GmbH | CR for TS 34.123-1: Correction of test case description 8.1.6.4 | CR |  |  |  | Revised in T1-040944 to add that the operator initiates a PDP context in step 1
T1-040581 |  | X | 8.8.3 | Ericsson | Correction to package 1 RRC test case 8.2.4.1a | CR | H |  |  | Approved
T1-040582 |  |  | 8.8.2.3 | Ericsson | Correction to PDCP test cases for lossless SRNS relocation | CR |  |  |  | Withdrawn
T1-040583 |  | -1 |  | Anritsu | Corrections to GCF P3 Test Cases 13.2.2.1 and 13.2.2.2 |  |  |  |  | Withdrawn
T1-040584 |  | X | 7.5.4 | Ericsson | Addition of details for RRM test case for GSM carrier RSSI | CR
T1-040585 |  | X | 8.8.1 | Sasken Communication Technologies Ltd | Correction to initial conditions of Idle Mode test case 6.2.1.6 | CR | H |  |  | Approved
T1-040586 |  | X | 8.8.1 | Sasken Communication Technologies Ltd | Changes to Test Requirement for Idle Mode test case 6.2.1.9 | CR |  |  |  | Withdrawn. The new test requirement will not work for subsequent loops of step e).
T1-040587 |  | X | 8.8.1 | Sasken Communication Technologies Ltd | Changes to test procedure of Idle Mode Cell Reselection test case 6.2.2.3 | CR |  |  |  | Revised in T1-040937 to use the 5.7.1 baseline
T1-040588 |  | X | 8.8.3 | Sasken Communication Technologies Ltd | Change to Test Requirement of Cell Reselection Case: 8.3.9.1 | CR |  |  |  | Revised in T1-040953. Deferred until later in the meeting to allow consideration of other test cases in the section
T1-040589 |  | X | 8.8.3 | Sasken Communication Technologies Ltd | Changes to test procedure of Cell Reselection Case 8.3.9.3 | CR | L | W |  | Approved
T1-040590 |  | X | 8.8.3 | Sasken Communication Technologies Ltd | Addition of 6 new Inter-RAT test cases. | CR |  |  |  | Revised in T1-040952
T1-040591 |  | X | 7.5 | Ericsson | Correction to default messages in Annex I of 34.121 | CR
T1-040592 |  | X | 8.9.1 | Ericsson | CR to 34.123-2 Rel-5: New HSDPA MAC-hs reset test case | CR |  |  |  | Approved
T1-040593 |  | X | 8.7.2 | Ericsson | CR to 34.108 REL-5: Corrections to default RRC messages | CR | L |  |  | Approved
T1-040594 |  | X | 8.8.3 | Ericsson | CR to 34.123-1 REL-5: Corrections to HSDPA RRC test cases | CR |  |  |  | Revised in T1-040967
T1-040595 |  | X | 8.8.3 | Ericsson | CR to 34.123-1 REL-5: New HSDPA RRC test cases | CR |  |  |  | Revised in T1-040974
T1-040596 |  | X | 8.9.1 | Ericsson | CR to 34.123-2 REL-5: New HSDPA RRC test cases | CR |  |  |  | Approved
T1-040597 |  | X | 8.8.10 | Ericsson | CR to 34.123-1 REL-5: Inclusion of details on A-GPS test cases | CR |  |  |  | To be merged
T1-040598 |  | X | 8.9.1 | Ericsson | CR to 34.123-2 [R99,REL-4,REL-5] New A-GPS test cases | CR |  |  |  | To be revised
T1-040599 |  |  | 1.2 | WG Chairman | T1#23 Agenda | AGENDA
T1-040600 |  | X | 1.3 | WG Chairman | T1#23 Meeting Schedule | AGENDA
T1-040601 |  | X | 2.1 | WG Chairman | Review of Leadership Team | INFO
T1-040602 |  |  | 4.1 | WG Chairman | Draft T1#22 Report | INPUT REPORT
T1-040603 |  | X | 4.2 | WG Chairman | T1 Status Report to T#23 | INPUT REPORT
T1-040604 |  | X | 4.3. | WG Chairman | TF 160 Status Report to T#23 | INPUT REPORT
T1-040605 |  | X | 4.5 | WG Chairman | Update on RCM | INPUT REPORT
T1-040606 |  | X | 4.8.1 | WG Chairman | Draft T#23 Report | INPUT REPORT
T1-040607 |  |  | 4.8.2 | WG Chairman | Post T#23 Comments | INPUT REPORT
T1-040608 |  | X | 4.8.3 | WG Chairman | SA#22 Report Summary for T
T1-040609 |  |  | 4.8.4 | WG Chairman | T Report to PCG#12 | INPUT REPORT
T1-040610 |  |  | 4.8.5 | WG Chairman | PCG Report | INPUT REPORT
T1-040611 |  |  | 4.8.6 | WG Chairman | OP Report | INPUT REPORT
T1-040612 |  | X | 4.8.7 | WG Chairman | Updated GCF Prioritisation List | INPUT REPORT
T1-040613 |  | X | 4.8.6 | WG Chairman | Post UAG#7 Comments | INPUT REPORT
T1-040614 |  | X | 8.3 | WG Chairman | GCF LS Migration from FDD R99 Mar 03 | LS
T1-040615 |  | X | 8.3 | WG Chairman | GCF LS Prose & TTCN Alignment at Verification | LS
T1-040616 |  | X | 8.3 | WG Chairman | GCF LS Sharing of Verification by T1 Members | LS
T1-040617 |  | X | 6.3 | WG Chairman | Future Meeting Schedule | MTG DETAILS: Meeting Details (invitation, participants list, host details, ...)
T1-040618 |  | X | 9.6 | WG Chairman | Draft Status Report to T Plenary | OUTPUT REPORT: Output Report (minutes, actions, decisions)
T1-040619 |  | X | 8.8.3 | Nokia | CR to 34.123-1 REL-5: Correction to package 4 RRC test cases 8.2.3.11, 8.2.6.11 and 8.2.6.12 | CR |  | W |  | Revised in T1-040945 for editorial error on cover sheet. Motorola asked if Nokia would check other similar test cases and see if the same change (cell reselection-> cell update would be required. Nokia offered to do this for the next meeting. It was also noted that a similar CR was required for 34.123-2. Nokia volunteered to raise this for this meeting.
T1-040620 |  | X | 8.8.10 | Qualcomm | Test Plan Development for A-GPS |  |  |  |  | Noted
T1-040621 |  | X | 8.8.10 | Qualcomm | CR to 34.123-1 R5: New test case 17.2.2.2 for UE-based A-GPS, nominal case of network-induced location request with assistance data | CR |  |  |  | To be merged
T1-040622 |  | X | 8.8.10 | Qualcomm | CR to 34.123-1 R5: New test case 17.2.4.1 for UE-based A-GPS, nominal case of mobile-terminated location request with assistance data | CR |  |  |  | To be merged
T1-040623 |  | X | 8.8.10 | Qualcomm | CR to 34.123-1 R5: New test case 17.2.4.2 for UE-based A-GPS, mobile-terminated location request with additional assistance data requested by mobile | CR |  |  |  | To be merged
T1-040624 | -1 |  |  | Panasonic | Correction to TC 8.1.2.2 (P1) |  |  |  |  | Withdrawn
T1-040625 |  | X | 8.8.3 | Motorola | Correction to number of reported cells in RRC P2 test case 8.4.1.7 |  | H |  |  | Approved.
T1-040626 |  |  | 8.8.3 | Motorola | Correction to Low Priority RRC Cell Change Order Test Cases |  | L |  |  | Approved
T1-040627 |  |  | 8.8.3 | Panasonic | Removal of 8.2.1.26 (P4) | CR | N | W |  | Approved
T1-040628 |  |  | 8.8.3 | Motorola | Correction to P4 RRC Cell Change Order Test Cases |  | L | W |  | Approved
T1-040629 |  |  | 8.8.3 | Motorola | Correction to P3 HCS test case 8.3.2.13 |  | H |  |  | Approved
T1-040630 |  |  | 8.8.3 | Motorola | Correction to P2 RRC test case 8.2.4.4 |  | N |  |  | Approved
T1-040631 |  |  | 8.8.3 | Motorola | Correction to P4 RRC UTRAN to GERAN Cell Reselection test cases |  | L | W |  | Approved
T1-040632 |  |  | 8.8.3 | Motorola | Correction to Low Priority RRC UTRAN to GERAN Cell Reselection test cases |  | L |  |  | Approved
T1-040633 |  |  | 8.8.3 | Motorola | Corrections to P2 RRC test case 8.3.2.4 |  | N |  |  | Approved
T1-040634 |  |  | 8.8.3 | Motorola | Corrections to P2 RRC test case 8.3.2.1 |  | H |  |  | Approved
T1-040635 |  |  | 8.8.3 | Motorola | Corrections to P2 RRC test case 8.4.1.18 |  | H |  |  | Approved
T1-040636 |  |  | 8.8.7 | Motorola | Correction to P4 GMM test case 12.4.1.1b |  |  |  |  | Revised in T1-040966. Postponed to allow the TC to be modified to NMO II so that a normal RAU is used.
T1-040637 |  |  | 8.8.3 | Motorola | Correction to P3 Inter Rat Measurement test cases |  | H |  |  | Approved
T1-040638 |  |  | 8.7.2 | Nokia, Nortel | Move of Annex B RAB combinations for Rel-5 contents to the correct place in the specification | CR |  |  |  | Withdrawn, the change is already covered in T1-040931
T1-040639 |  |  | 8.8.12 | CCSA | Errors correction in section 8.4.1.7A for TDD OF TS34.123-1 |  |  |  |  | Approved
T1-040640 |  |  | 8.8.12 | CCSA | Errors correction in section 8.4.1.29 of TS34.123-1 |  |  |  |  | Approved
T1-040641 |  |  | 8.8.12 | CCSA | DR-34.123-8.1.6.3: To add the description of 'Primary CCPCH info' (for TDD) in 8.1.6.3 |  |  |  |  | Approved
T1-040642 |  |  | 8.8.12 | CCSA | DR-34.123-8.2.6.8: To add the descriptionof 'Primary CCPCH info'(for TDD) in 8.2.6.8 |  |  |  |  | Approved
T1-040643 |  |  | 8.7.3 | CCSA, Siemens | Corrections to LCR TDD RABs |  |  |  |  | Revised in T1-040926
T1-040644 |  |  | 8.8.12 | CCSA | CR-34.123_1-8.3.1.4: Errors correction in section 8.3.1.4.4 of TS34.123-1 |  |  |  |  | Approved
T1-040645 |  |  | 8.8.12 | CCSA | CR-34.123_1-8.4.1.2a: Errors correction in section 8.4.1.2a of TS34.123-1 |  |  |  |  | Approved
T1-040646 |  |  | 8.8.3 | Panasonic | Corrections to 8.2.1.27 (Low priority) | CR | N |  |  | Approved
T1-040647 |  |  | 8.8.1 | Ericsson | General corrections to section 6 of 34.123-1 (idle mode) | CR |  |  |  | Approved
T1-040648 |  |  | 8.8.3 | Sasken Communication Technologies Limited, MCC Task 160 | Corrections in Security Mode Command for 8.1.7.1 and 8.1.7.2 test cases. | CR | H | W |  | Approved
T1-040649 |  |  | 8.7.2 | Ericsson | CR to 34.108 Rel-5: Changes to establish one version of 34.108 covering all releases | CR |  |  |  | Revised in T1-040930
T1-040650 |  |  | 6.8 | Ericsson | Draft CR to 34.109 Rel-5 to increase maximum number of loopback entities
T1-040651 |  |  | 8.8.3 | Ericsson | CR to TS 34.123-1 R5: Correction to P1 RRC TC 8.4.1.1. | CR | H |  |  | Approved
T1-040652 | -1 |  |  | Nortel Networks, Ericsson, ETSI | Change of default LAC/RAC for inter-RAT test cases |  |  |  |  | Withdrawn
T1-040653 | -1 |  |  | Nortel Networks, Ericsson, ETSI | Change of default LAC/RAC for inter-RAT test cases - Rel-4 |  |  |  |  | Withdrawn
T1-040654 |  | X | 8.7.1 | Nortel Networks, Ericsson, ETSI | CR to 34.108 R99: Change of default LAC/RAC for inter-RAT test cases | CR |  |  |  | Approved
T1-040655 |  | X | 8.7.1 | Nortel Networks, Ericsson, ETSI | CR to 34.108 Rel-4: Change of default LAC/RAC for inter-RAT test cases | CR |  |  |  | Approved
T1-040656 |  | X | 8.7.2 | Nortel Networks, Ericsson, ETSI | CR to 34.108 Rel-5: Change of default LAC/RAC for inter-RAT test cases | CR | H |  |  | Approved
T1-040657 |  |  | 8.6.1 | InterDigital Communications Corp. | Summary of HCR TDD CRs | INFO |  |  |  | Noted
T1-040658 |  |  | 8.8.13 | InterDigital Communications Corp. | Add HCR TDD content of Inter-frequency measurement for event 2A | CR |  |  |  | Approved
T1-040659 |  |  | 8.8.13 | InterDigital Communications Corp. | Add HCR TDD content of Inter-frequency measurement for event 2B and 2E | CR |  |  |  | Approved
T1-040660 |  |  | 8.8.13 | InterDigital Communications Corp. | Add HCR TDD content of Inter-frequency measurement for event 2D and 2F | CR |  |  |  | Revised in T1-040978
T1-040661 |  |  | 8.8.13 | InterDigital Communications Corp. | Add HCR TDD content for UE internal measurement, event 6c | CR |  |  |  | Approved
T1-040662 |  |  | 8.8.13 | InterDigital Communications Corp. | Add HCR TDD content for UE internal measurement, event 6d | CR |  |  |  | Approved
T1-040663 |  |  | 8.8.13 | InterDigital Communications Corp. | Add HCR TDD content for UE internal measurement, event 6e | CR |  |  |  | Approved
T1-040664 |  |  | 8.8.13 | InterDigital Communications Corp. | Adding of new test cases for events 1G for HCR TDD | CR |  |  |  | Approved
T1-040665 |  |  | 8.8.3 | Anite | Revisions to Package 3 measurement test cases 8.4.1.31 and 8.4.1.40 | CR |  |  |  | Revised in T1-040943 to fix editorial mistake in table headers
T1-040666 |  |  | 8.8.13 | InterDigital Communications Corp. | Tests for HCR TDD RAB combinations TS34.123-1 18.2 | CR |  |  |  | Approved
T1-040667 |  |  | 8.8.2.2 | Anite | Re-instatement of Test Requirements to meet the Test Purpose in Package 1 TCs 7.2.3.24 and 7.2.3.27 | CR |  |  |  | Withdrawn, Merged
T1-040668 |  |  | 8.8.3 | Anite | Corrections to specific message contents of Package 1 test case 8.1.2.9 to support CS Domain | CR | N |  |  | Approved
T1-040669 |  |  | 8.8.3 | Anite | Corrections to Table 8.3.7-1 in relation to Package 2 test cases 8.3.7.x | CR |  |  |  | Revised in T1-040942 to include section header.
T1-040670 |  |  | 8.8.4 | Anite | Add Statement to Clause 9 regarding GMM signalling for UEs supporting PS/CS mode of operation | CR |  | W |  | Merged into T1-040949
T1-040671 |  |  | 8.8.5 | Anite | Correction to Conformance Requirement for P3 CC NAS TCs regarding support for Prolonged Clearing Procedure | CR | N |  |  | Approved
T1-040672 |  |  | 8.7.2 | Anite | CR to 34.108 Rel-5: Modification to default DPCCH_Power_offset value | CR |  |  |  | Widthdrawn, change included in T1-040931
T1-040673 |  |  | 8.7.2 | Anite | CR to 34.108 Rel-5: Contents of Physical Channel Reconfiguration message modified to incorporate transition to URA_PCH or CELL_PCH | CR | H |  |  | Approved
T1-040674 |  |  | 8.8.3 | Anite | Correction to RRC Package 2 TC 8.4.1.17 on Measurement Reporting Interval | CR | N |  |  | Approved
T1-040675 |  |  | 8.9.1 | Anite | Change to the applicability table for 8.3.7.2 / 8.3.7.2a and 8.3.7.3 / 8.3.7.3a following splitting of these TCs according to supported data rates | CR |  |  |  | Approved
T1-040676 |  |  | 8.8.5 | Anite | Correction to Conformance Requirement for P4 CC NAS TCs regarding support for Prolonged Clearing Procedure | CR |  |  |  | Postponed to T1#24
T1-040677 |  |  | 8.8.5 | Anite | Correction to Conformance Requirement for Low Priority CC NAS TCs regarding support for Prolonged Clearing Procedure | CR |  |  |  | Postponed to T1#24
T1-040678 |  |  | 8.8.3 | Sasken Communication Technologies Limited | Correction to 8.3.4.2 test case at Step 6 for Measurement Report Message | CR | N | W |  | Approved
T1-040679 |  |  | 8.8.6 | Sasken Communication Technologies Limited | Corrections to 11.3.1 and 11.3.2 testcases | CR |  |  |  | Withdrawn. Discussion document was noted. T1 decision was to leave the prose so that Detach is only expected for UEs that do not support attach at power on. It was also noted that the TTCN was not incorrect in allowing this, but at some point in the future should be aligned with the prose.
T1-040680 |  |  | 8.8.3 | Sasken Communication Technologies Limited | Correction for RRC Transaction Identifier in test cases 8.1.6.1 and 8.1.6.2 | CR | L | W |  | Approved
T1-040681 |  |  | 8.8.3 | Sasken Communication Technologies Limited | Correction to New C-RNTI value at Step5 in 8.3.1.11 testcase. | CR | H | W |  | Approved
T1-040682 |  |  | 8.8.2.1 | Sasken Communication Technologies Limited | Correction to prose for test case 7.1.1.1 | CR | N |  |  | Approved
T1-040683 |  | X | 8.7.1 | Anritsu | Corrections to Contents of Scheduling Block 1 (FDD) | CR
T1-040684 |  | X | 8.7.1 | Anritsu | Corrections to Contents of PHYSICAL CHANNEL RECONFIGURATION message: AM or UM | CR
T1-040685 |  | X | 8.7.1 | Anritsu | Corrections to Contents of RRC CONNECTION SETUP message: UM | CR
T1-040686 |  | X | 7.x | Anritsu | Corrections to Contents of RADIO BEARER SETUP message: BTFD RMC | CR
T1-040687 |  | X | 7.x | Anritsu | RADIO BEARER SETUP message (FDD) for Test Loop Mode2 | CR
T1-040688 |  | X | 7.5.3 | Anritsu | Clarification of FDR | CR
T1-040689 |  | X | 7.5.4.1 | Anritsu | Addition of CELL_UPDATE CONFIRM Message and URA_UPDATE CONFIRM Message | CR
T1-040690 |  | X | 7.5.4.2 | Anritsu | Correction to the pathloss indicator in measurement control messages | CR
T1-040691 |  | X | 7.5.4.2 | Anritsu | Addition of MEASUREMENT CONTROL message and ACTIVESET UPDATE meesage in 8.5.1 | CR
T1-040692 |  | X | 7.5.4.2 | Anritsu | Correction to 8.4.1.1 RRC cnnection control test 1 | CR
T1-040693 |  | X | 7.5.4.2 | Anritsu | Clarification of the Monitor List Size | CR
T1-040694 |  | X | 7.5.4.4 | Anritsu | Correction to URA identity for reselection in Cell URA_PCH | CR
T1-040695 |  | X | 7.5.5 | Anritsu | Update of F1.5 | CR
T1-040696 |  |  | 8.10.4 | Motorola | Verification results of Package 2 test cases – V |  |  |  |  | Noted
T1-040697 |  |  | 8.10.4 | Motorola | Verification results of Package 3 test cases – II |  |  |  |  | Noted
T1-040698 |  |  | 8.10.4 | Motorola | Verification results of Package 4 test cases – I |  |  |  |  | Noted
T1-040699 |  | X | 7.7.5 | NTT DoCoMo Inc. | Correction of channel number for UMTS800(band VI) (CR to 34.121) | CR
T1-040700 |  | X | 7.7.5 | NTT DoCoMo Inc. | Correction of Spurious Emissions for UMTS800(band VI) (CR to 34.121) | CR
T1-040701 |  | X | 7.7.5 | NTT DoCoMo Inc. | Correction of reference test frequencies for UMTS800(band VI) (CR to 34.108 Rel-5) | CR
T1-040702 |  | X | 7.7.5 | NTT DoCoMo Inc. | Correction of reference test frequencies for UMTS800(band VI) (CR to 34.108 Rel-4) | CR
T1-040703 |  | X | 7.7.5 | NTT DoCoMo Inc. | Correction of reference test frequencies for UMTS800(band VI) (CR to 34.108 R99) | CR
T1-040704 |  | X | 8.8.1 | Anite, Anritsu, Ericsson, Motorola, Nokia, Racal Instruments | Corrections to P2 PLMN and RAT selection test cases in Multi-mode environment (2G/3G case) | CR |  |  |  | Revised in T1-040971
T1-040705 |  | X | 8.9.1 | Nokia | New PIXIT statement | CR |  |  |  | Approved
T1-040706 |  | X | 8.8.12 | CCSA | Difference and Corresponding Effect Analysis to Terminal Conformance Test between FDD and LCR TDD in Access Stratum
T1-040707 |  | X | 8.8.4 | Nokia | Correction to Package 2 test case 9.4.2.3 | CR |  |  |  | Revised in T1-040961
T1-040708 |  | X | 8.8.6 | Sasken Communication Technologies Limited. | Discussion of Correction of SM Test Case 11.1.1.1 in relation to Modify PDP Context Procedure. (CR T1-040409) | OTHER |  |  |  | Noted. An alternative of removing the mdofy PDP context procedure completely was agreed. It was also agreed that the current implementation is not incorrect, and so modifications to TCs 11.1.1.1 and 11.1.1.1a are not considered urgent.
T1-040709 |  | X | 8.8.7 | Ericsson | Correction to package 3 GMM test case 12.4.2.5a | CR |  |  |  | Revised in T1-040950
T1-040710 |  | X | 8.8.3 | Panasonic | Editorial correction to 8.2.3.22 (Low priority) | CR | N |  |  | Approved
T1-040712 |  | X | 8.8.3 | Panasonic | Corrections to SRNS relocation RRC test cases | CR |  |  |  | Revised in T1-040975
T1-040713 |  | X | 8.8.2.3 | Panasonic | Corrections to SRNS relocation PDCP test cases | CR |  |  |  | Revised in T1-040939
T1-040714 |  | X | 8.8.3 | Panasonic | Addition of new SRNS relocation test cases | CR |  |  |  | Revised in T1-040976
T1-040715 |  | X | 8.8.3 | Panasonic | Addition of new SRNS relocation (radio link failure) test cases | CR |  |  | 2004-05-24 | Deferred to reflector
T1-040716 |  | X | 8.8.7 | Sony Ericsson Mobile Communications Japan, Inc. | Modification for GMM test cases (P4 and low priority test cases) |  |  |  |  | To be merged
T1-040717 |  | X | 8.8.8 | Ericsson | Correction to low priority radio bearer test cases (minimum set of TFCS) | CR |  |  |  | Revised in T1-040947
T1-040718 |  | X | 8.8.3 | Ericsson | Correction to Table 8.3.7-1 for inter-RAT handover | CR |  |  |  | Widthdrawn. Changes included in T1-040669.
T1-040719 |  | X | 7.5.3 | NEC | Correction to BTFD test case 7.10 | CR
T1-040720 |  | X | 7.5.4.1 | NEC | Removal of [] for UE transmit power test case 8.7.3C | CR
T1-040721 |  | X | 7.5 | NEC | Proposed addition of downlink code allocation table to 34.121 Annex | CR
T1-040722 |  | X | 8.8.4 | Rohde & Schwarz | CR to 34.123-1 Rel-5: Corrections to MM test cases to include GMM procedures | CR |  | W |  | Merged with T1-040670 into T1-040949 to include Anite statement in Clause 9. Rewording of comments in sequence tables to make it clear they are not a requirement of the test case. Remove Detach Request in step 9 of 9.4.2.1.
T1-040723 | -1 |  |  | Rohde & Schwarz | CR to 34.123-1 Rel-5: Corrections to MM test cases to emergency call support and authentication procedures |  |  |  |  | Withdrawn
T1-040724 |  | X | 8.8.4 | Rohde & Schwarz | CR to 34.123-1 Rel-5: Corrections to MM test cases to emergency call support and authentication procedures | CR | N |  |  | Approved
T1-040725 |  | X | 8.8.4 | Rohde & Schwarz | CR to 34.123-1 Rel-5: Correction to MM test case 9.4.8 | CR |  |  |  | Revised in T1-040948.
T1-040726 |  | X | 8.8.9 | Rohde & Schwarz | CR to 34.123-1 Rel-5: Correction to SMS test case 16.1.1 | CR |  |  |  | Merged in T1-040777
T1-040727 |  | X | 7.x | Motorola | Correction to 7.11 (Demodulation of paging channel (PCH)) | CR
T1-040728 |  | X | 7.x | Motorola | Correction to 8.7.6 UE Rx-Tx time difference | CR
T1-040729 |  | X | 7.x | Motorola | Correction to Transmit Off Power | CR
T1-040730 |  | X | 7.x | Motorola | New TPC combining in SHO test case | CR
T1-040731 |  | X | 8.8.3 | Rohde & Schwarz | CR to 34.123-1 Rel-5: Correction to package 3 RRC test case 8.4.1.26 | CR | N |  |  | Approved
T1-040732 |  | X | 8.8.3 | Rohde & Schwarz | CR to 34.123-1 Rel-5: Correction to package 3 RRC test case 8.2.4.1a | CR | N |  |  | Approved
T1-040733 |  | X | 7.x | Motorola | New test case for 9.2.2 Open Loop Diversity Performance | CR
T1-040734 |  | X | 7.x | Motorola | New test case for 9.2.3 Closed Loop Diversity Performance | CR
T1-040735 |  | X | 7.x | Motorola | New test case for 9.4 HS-SCCH Detection Performance | CR
T1-040736 |  | X | 7.x | Motorola | Modification to Demodulation of DCH in open-loop transmit diversity mode test case | CR
T1-040737 |  | X | 8.9.1 | Panasonic | Update new SRNS test cases to applicability table | CR |  |  |  | Revised in T1-040775
T1-040738 |  |  | 7.5.2 | Siemens (Roke Manor) | Maximum RX input level for HSDPA | CR
T1-040739 |  |  | 7.5.1 | Siemens (Roke Manor) | UE Transmit Timing (test equipment allowance) | CR
T1-040740 |  |  | 7.5 | Siemens (Roke Manor) | RF Progress Spreadsheet | INPUT REPORT
T1-040741 |  |  | 7.7 | Siemens (Roke Manor) | Measuring Throughput in a Fading Channel
T1-040742 |  | X | 8.3 | GP-041207 | LS on Verification and Approval of GERAN to UTRAN TTCN Test Cases | LS |  |  |  | Noted
T1-040743 |  | X | 8.3 | N1-040378 | LS on Clarification of optional TMSI Status IE in Attach Request and Routing Area Update Request Messages | LS |  |  |  | Noted
T1-040744 |  | X | 8.3 | N1-040441 | LS on HPLMNAcT field | LS |  |  |  | Noted. Discussed 3 options. Use old behaviour, leave test cases out, or apply new CRs. Decision deferred to later in the meeting
T1-040745 |  | X | 8.3 | N1-040470 | LS on Permissibility of Separate RRC Connections for Sequential CS and PS Registration | LS |  |  |  | Noted. Waiting for a response from RAN2
T1-040746 |  | X | 7.x | R4-040111 | Response LS to RAN4 on clarification of measurement control for FDD/FDD Inter-frequency Hard Handover and alignment with 34.121 | LS
T1-040747 |  | X | 7.x | R4-040146 | LS on equipment complexity for AGPS testing | LS
T1-040748 |  | X | 7.x | S4-040154 | Reply LS on Harmonisation of AMR Configurations | LS
T1-040749 |  | X | 8.3 | T3-040295 | LS on Support of multiple HPLMN codes in EF_HPLMNwAcT | LS |  |  |  | Noted (See 744)
T1-040750 |  | X | 8.8.14. | Nortel Networks, ETSI | CR to 34.123-1 (Annex): new test postamble for inter-RAT handover/cell change test cases | CR |  |  |  | Revised in T1-040779
T1-040751 |  | X | 8.8.3 | Panasonic | Corrections to uplink message with measurement results on RACH (Revision of T1-040711) | CR |  | W |  | Not approved. It needs futher investigation whether the UEs will ever send an RRC connection setup request longer than the maximum under the default intial conditions for conformance tests. In particular this should be investigated for R5.
T1-040752 |  |  | 7.7.4 | Ericsson | CR to 34.108 R99: Addition af details for generic setup procedures for FDD RF testing | CR
T1-040753 |  |  | 7.7.4 | Ericsson | CR to 34.108 REL-4: Addition af details for generic setup procedures for FDD RF testing | CR
T1-040754 |  |  | 7.7.4 | Ericsson | CR to 34.108 REL-5: Addition af details for generic setup procedures for FDD RF testing | CR
T1-040755 |  |  | 8.6.1 | CCSA | summary for TDD CRs |  |  |  |  | Noted
T1-040756 |  | X | 8.9.1 | Sasken Communication Technologies Ltd., | Addition of 6 new Inter-RAT test cases. | CR |  |  | 2004-05-24 | Deferred to reflector
T1-040757 |  |  | 8.10.3 | ETSI Secretariat | TTCN status report wk19 | INPUT REPORT
T1-040758 |  | X | 8.8.3 | Nokia | Correction to low priority TC 8.3.11.3 | CR | L |  | 2004-05-24 | Deferred to reflector
T1-040759 |  |  | 8.8.7 | Anritsu Ltd. | 34.123-1 Correction to GCF P2 Test Case 12.4.2.1 | CR |  |  |  | Withdrawn
T1-040760 |  | X | 7.7.3 | Nokia | Discussion on problems in 9.2.X tests
T1-040761 |  | X | 8.10.1 | Anite | Clarification of Section 8.5.1 Authentication: Explicitly stating that Authentication after IDT is an optional/dependent procedure | CR |  |  |  | Approved
T1-040762 |  | X | 7.7.3 | NEC | Mark one testpoint for HSDPA H-Set 5 as not testable | CR
T1-040763 |  | X | 8.3 | MCC | LS regarding GERAN 3 #18 CRs to test cases that are thought to be of interest to T1 |  |  |  |  | Noted
T1-040764 |  | X | 8.3 | MCC | LS regarding GERAN 3 #19 CRs to test cases that are thought to be of interest to T1 |  |  |  |  | Noted
T1040766 |  |  | 8.5.2 | Rohde & Schwarz | Approval and validation of GCF P1 to P4 test cases |  |  |  |  | Noted
T1-040900 |  |  | 8.4. | NTT DoCoMo Inc. | Status of E-mail non-TTCN CR approvals | INPUT REPORT |  |  |  | Noted
T1-040901 |  |  | 8.7.2 | NTT DoCoMo Inc. | Correction of different parameters of RB Setup for HSDPA | CR |  |  |  | Postponed. LS will be drafted to RAN2 to check parameters first.
T1-040902 |  |  | 8.7.2 | Sasken Communication Technologies Limited | Physical channel parameters for AM RLC 7 bit Length Indicator TestCases (Rel-5) | CR | N |  |  | Approved
T1-040903 |  |  | 8.7.2 | Sasken Communication Technologies Limited, MCC Task 160 | Corrections to the default contents of Security Mode Command (Rel-5) | CR | H |  |  | Approved
T1-040904 |  |  | 8.7.1 | Anite | CR to 34.108 Rel-99: Modification to default DPCCH_Power_offset value | CR |  |  |  | Widthdrawn, change included in T1-040931
T1-040905 |  |  | 8.7.1 | Anite | CR to 34.108 Rel-4: Modification to default DPCCH_Power_offset value | CR |  |  |  | Widthdrawn, change included in T1-040931
T1-040906 |  |  | 8.7.1 | Anite | CR to 34.108 Rel-99: Contents of Physical Channel Reconfiguration message modified to incorporate transition to URA_PCH or CELL_PCH | CR |  |  |  | Approved
T1-040907 |  |  | 8.7.1 | Anite | CR to 34.108 Rel-4: Contents of Physical Channel Reconfiguration message modified to incorporate transition to URA_PCH or CELL_PCH | CR |  |  |  | Approved
T1-040908 |  |  | 8.7.1 | Anritsu | Corrections to Contents of Scheduling Block 1 (FDD) | CR
T1-040909 |  |  | 8.7.1 | Anritsu | Corrections to Contents of Scheduling Block 1 (FDD) | CR
T1-040910 |  |  | 8.7.1 | Anritsu | Corrections to Contents of PHYSICAL CHANNEL RECONFIGURATION message: AM or UM | CR
T1-040911 |  |  | 8.7.1 | Anritsu | Corrections to Contents of PHYSICAL CHANNEL RECONFIGURATION message: AM or UM | CR
T1-040912 |  |  | 8.7.1 | Anritsu | Corrections to Contents of RRC CONNECTION SETUP message: UM | CR
T1-040913 |  |  | 8.7.1 | Anritsu | Corrections to Contents of RRC CONNECTION SETUP message: UM | CR
T1-040914 |  |  | 7.x | Anritsu | Corrections to Contents of RADIO BEARER SETUP message: BTFD RMC | CR
T1-040915 |  |  | 7.x | Anritsu | Corrections to Contents of RADIO BEARER SETUP message: BTFD RMC | CR
T1-040916 |  |  | 7.x | Anritsu | RADIO BEARER SETUP message (FDD) for Test Loop Mode2 | CR
T1-040917 |  |  | 7.x | Anritsu | RADIO BEARER SETUP message (FDD) for Test Loop Mode2 | CR
T1-040918 |  |  | 8.8.2.2 | Anite, Sasken | Re-instatement of Test Requirements to meet the Test Purpose in Package 1 TCs 7.2.3.24 and 7.2.3.27 | CR |  |  |  | Revised in T1-040938 to remove step 2) of test requirements on 7.2.3.24
T1-040919 |  |  | 8.8.3 | Panasonic | Corrections to test case 8.3.1.30 (low priority) | CR | N |  |  | Approved
T1-040920 |  |  | 8.8.3 | Racal & MCC 160 | System information 1 modification for FACH, DCH | CR |  |  |  | Revised in T1-040941 to move SIB1 change into initial conditions.
T1-040921 |  |  | 8.8.4 | Anite | Correction to clause 9.3.1 | CR | N |  |  | Approved
T1-040922 |  |  | 8.8.7 | Sasken, SEMC | Merge of documents 547 & 716 |  |  |  |  | Revised as T1-040951
T1-040923 |  |  | 8.8.10 | Ericsson, Motorola & Qualcomm | Merge of 597, 621, 622, 623 |  |  |  |  | Revised as T1-040955
T1-040924 |  |  | 8.9.1 | Ericsson, Motorola & Qualcomm | CR to 34.123-2 [R99,REL-4,REL-5] New A-GPS test cases | CR |  |  |  | Approved
T1-040925 |  |  | 8.5.1 | Anite | Updated Proposed change to PRD-12 on e-mail handling of TTCN CRs
T1-040926 |  |  | 8.7.3 | CCSA, Siemens | Corrections to LCR TDD RABs (Rel4) | CR |  |  |  | Approved
T1-040927 |  |  | 8.7.1 | Nokia | CR to 34.108 R99: Default setting of NMO | CR |  |  |  | Not approved at this meeting
T1-040928 |  |  | 8.7.1 | Nokia | CR to 34.108 Rel4: Default setting of NMO | CR |  |  |  | Not approved at this meeting
T1-040929 |  |  | 8.7.1 | Nokia | CR to 34.108 Rel5: Default setting of NMO | CR |  |  |  | Not approved at this meeting
T1-040930 |  |  | 8.7.2 | Ericsson | CR to 34.108 Rel-5: Changes to establish one version of 34.108 covering all releases | CR |  |  |  | Wil be revised to add Rel indicator to the RAB configurations in the list of combinations.Need to check if the new DPCH power offset should be applied to RF tests.
T1-040931 |  |  | 8.7.2 | Ericsson | CR to 34.108 Rel-5: Changes to establish one version of 34.108 covering all releases | CR |  |  |  | Approved
T1-040932 |  |  | 8.7.1 | ETSI Secretariat | CR to 34.108 Rel-99: Changes to establish one version of 34.108 covering all releases | CR |  |  |  | Approved
T1-040933 |  |  | 8.7.1 | ETSI Secretariat | CR to 34.108 Rel-4: Changes to establish one version of 34.108 covering all releases | CR |  |  |  | Approved
T1-040934 |  |  | 8.7.2 | Ericsson | CR to 34.108 Rel-5: Addition of generic test procedure for AS test cases using the test loop | CR | N |  |  | Approved.
T1-040935 |  |  | 8.7.3 | CCSA, Siemens | Corrections to LCR TDD RABs (Rel5) | CR |  |  |  | Approved
T1-040936 |  |  | 8.12.4 | Qualcomm & NTT DoCoMo | Draft LS to RAN2 on HSDPA RAB configuration parameters | LS
T1-040937 |  |  | 8.8.1 | Sasken Communication Technologies Ltd | Changes to test procedure of Idle Mode Cell Reselection test case 6.2.2.3 | CR |  |  |  | Approved.
T1-040938 |  |  | 8.8.2.2 | Anite, Sasken | Re-instatement of Test Requirements to meet the Test Purpose in Package 1 TCs 7.2.3.24 and 7.2.3.27 | CR | H |  |  | Approved.
T1-040939 |  |  | 8.8.2.3 | Panasonic | Corrections to SRNS relocation PDCP test cases | CR |  |  |  | Revised in T1-040973 to remove Ciphering IXIT and to remove CS from initial conditions.
T1-040940 |  |  | 8.10.1 | MCC task 160 | GERAN generic procedures and TTCN encoding rules for CSN.1 specific encoding | CR |  |  | 2004-05-24 | Deferred to reflector
T1-040941 |  |  | 8.8.3 | Racal & MCC 160 | System information 1 modification for FACH, DCH | CR | H |  |  | Approved.
T1-040942 |  |  | 8.8.3 | Anite | Corrections to Table 8.3.7-1 in relation to Package 2 test cases 8.3.7.x | CR | N |  |  | Approved.
T1-040943 |  |  | 8.8.3 | Anite | Revisions to Package 3 measurement test cases 8.4.1.31 and 8.4.1.40 | CR | H |  |  | Approved.
T1-040944 |  |  | 8.8.3 | CETECOM GmbH | CR for TS 34.123-1: Correction of test case description 8.1.6.4 | CR | N |  |  | Approved.
T1-040945 |  |  | 8.8.3 | Nokia | CR to 34.123-1 REL-5: Correction to package 4 RRC test cases 8.2.3.11, 8.2.6.11 and 8.2.6.12 | CR | N | W |  | Approved
T1-040946 |  |  | 8.9.1 | Nokia | CR to 34.123-2 REL-5: Correction to titles of package 4 RRC test cases 8.2.3.11, 8.2.6.11 and 8.2.6.12 | CR |  |  |  | Approved
T1-040947 |  |  | 8.8.8 | Ericsson | Correction to low priority radio bearer test cases (minimum set of TFCS) | CR | L |  |  | Approved
T1-040948 |  |  | 8.8.4 | Rohde & Schwarz | CR to 34.123-1 Rel-5: Correction to MM test case 9.4.8 | CR |  | W |  | Revised in T1-040954. Postponed to later in the meeting to allow revision to ensure the starting conditions for the test are correct.
T1-040949 |  |  | 8.8.4 | Rohde & Schwarz | CR to 34.123-1 Rel-5: Corrections to MM test cases to include GMM procedures | CR | H |  |  | Approved
T1-040950 |  |  | 8.8.7 | Ericsson | Correction to package 3 GMM test case 12.4.2.5a | CR | H |  |  | Approved
T1-040951 |  |  | 8.8.7 | Sasken, SEMC, Nokia | Modification for GMM test cases (P4 and low priority test cases) | CR | L |  |  | Approved
T1-040952 |  |  | 8.8.3 | Sasken Communication Technologies Ltd | Addition of 6 new Inter-RAT test cases. | CR |  |  |  | Revised in T1-040977
T1-040953 |  |  | 8.8.3 | Sasken Communication Technologies Ltd | Change to Test Requirement of Cell Reselection Case: 8.3.9.1 | CR |  |  |  | Revised in T1-040979
T1-040954 |  |  | 8.8.4 | Rohde & Schwarz | CR to 34.123-1 Rel-5: Correction to MM test case 9.4.8 | CR | H |  |  | Approved
T1-040955 |  |  | 8.8.10 | Ericsson, Motorola & Qualcomm | CR to 34.123-1 REL-5; New A-GPS test cases | CR |  |  |  | Approved
T1-040956 |  |  | 8.8.4 | Sasken Communication Technologies Limited | Correction to package 2 MM testcase 9.1 to align with TTCN implementation. | CR | N |  |  | Approved
T1-040957 |  |  | 8.12.4 | Qualcomm & NTT DoCoMo | Draft LS to RAN2 on HSDPA RAB configuration parameters | LS
T1-040958 |  |  | 8.8.2.1 | Rohde & Schwarz | CR to 34.123-1 Rel 5: Correction to package 2 MAC test case 7.1.3.1 | CR | N |  |  | Approved
T1-040959 |  |  | 8.8.3 | Rohde & Schwarz | CR to 34.123-1 Rel 5: Correction to package 2 RRC test case 8.4.1.2 | CR |  |  | 2004-05-24 | Deferred to reflector
T1-040960 |  |  | 8.9.1 | NEC | CR to 34.123-2: Applicability update for TC 11.1.2 | CR |  |  |  | Approved
T1-040961 |  |  | 8.8.4 | Nokia | Correction to Package 2 test case 9.4.2.3 | CR |  |  | 2004-05-24 | Deferred to reflector
T1-040962 |  |  | 8.8.6 | Nokia | Correction to Package 1 SM TC 11.3.1 RAB release location | CR | H |  |  | Approved
T1-040963 |  |  | 8.8.6 | Nokia | Correction to Package 1 SM TC 11.3.2 RAB release location | CR | H |  |  | Approved
T1-040964 |  |  | 8.8.4 | Anritsu Limited | Corrections to Package 2 test case 9.4.2.4 Procedure 2 | CR | H |  |  | Approved
T1-040965 |  |  | 8.8.6 | NEC | CR to TS 34.123-1 Rel-5: Correction to low priority SM TC 11.1.2 | CR |  |  |  | Revised in T1-040980
T1-040966 |  |  | 8.8.7 | Motorola | Correction to P4 GMM test case 12.4.1.1b | CR | L |  |  | Approved
T1-040967 |  |  | 8.8.3 | Ericsson | CR to 34.123-1 REL-5: Corrections to HSDPA RRC test cases | CR | L |  |  | Approved
T1-040968 |  |  | 8.8.9 | Sasken Communication Technologies Limited | Correction to Package III SMS Test Case 16.2.1 | CR | H |  |  | Approved
T1-040969 |  |  | 8.8.9 | Rohde & Schwarz, Sasken Communications | CR to 34.123-1 Rel-5: Correction to SMS test case 16.1.1 | CR | H |  |  | Approved
T1-040970 |  |  | 8.8.11 | Rohde & Schwarz | iWD for TS 34.123 tests not ready for T1 approval
T1-040971 |  |  | 8.8.1 | Anite, Anritsu, Ericsson, Motorola, Nokia, Racal Instruments, Sasken Communications | Corrections to P2 PLMN and RAT selection test cases in Multi-mode environment (2G/3G case) | CR | H |  |  | Approved
T1-040972 |  |  | 9.3 | Racal | LS to TSG-T on accepting changes to Idle mode test cases implementing allowed R6 behaviour in R99 UEs/ | LS
T1-040973 |  |  | 8.8.2.3 | Panasonic | Corrections to SRNS relocation PDCP test cases | CR |  |  |  | Approved
T1-040974 |  |  | 8.8.3 | Ericsson | CR to 34.123-1 REL-5: New HSDPA RRC test cases | CR | L |  |  | Approved
T1-040975 |  |  | 8.8.3 | Panasonic | Corrections to SRNS relocation RRC test cases | CR | L |  |  | Approved
T1-040976 |  |  | 8.8.3 | Panasonic | Addition of new SRNS relocation test cases | CR | L |  |  | Approved | T1-040952
T1-040977 |  |  | 8.8.3 | Sasken Communication Technologies Ltd | Addition of 6 new Inter-RAT test cases. | CR |  |  | 2004-05-24 | Deferred to reflector
T1-040978 |  |  | 8.8.13 | InterDigital Communications Corp. | Add HCR TDD content of Inter-frequency measurement for event 2D and 2F | CR |  |  |  | Approved | T1-040660
T1-040979 |  |  | 8.8.3 | Sasken Communication Technologies Ltd | Change to Test Requirement of Cell Reselection Case: 8.3.9.1 | CR | L |  |  | Approved
T1-040980 |  |  | 8.8.6 | NEC | CR to TS 34.123-1 Rel-5: Correction to low priority SM TC 11.1.2 | CR | L |  |  | Approved
T1-040981
T1-040982
T1-040983
T1-040984
T1-040985
T1-040986
T1-040777 |  |  | 8.8.9 | Rohde & Schwarz | CR to 34.123-1 Rel-5: Correction to SMS test case 16.1.1 | CR |  |  |  | Revised in T1-040969
T1-040779 |  |  | 8.8.14. | Nortel Networks, ETSI | CR to 34.123-1 (Annex): new test postamble for inter-RAT handover/cell change test cases | CR |  |  | 2004-05-24 | Deferred to the reflector
T1-040775 |  |  | 8.9.1 | Panasonic | Update new SRNS test cases to applicability table | CR |  |  |  | Approved
END

## Sheet2
Filter